## Structure
Client | Server (flask) | Database (SQLite) | External Data
html (3): - bootstrap - (think about resources page/links) | root route (app.py) = homepage route page 2 route page 3 | SQLite file | pandas notebook with all sources and dfs
javascript (3): - leaflet - d3 - plotly - event handlers | inside root route: (mars HW) - render_template - index.html inside templates folder - api call to database | input data (pandas) - ERD diagram - push data into db with primary key as separate tables - sqlalchemy | education/crime/ tech jobs available or where tech jobs available

## Sheet5
Task | Point | Due | Status | Notes
Put data in SQLite | Everyone in pandas nb | 2021-04-28 |  | census, salaries, incomes done
app.py (flask) template - using basic html | Sara |  | Done
index.html with bootstrap + navbar + etc. | Caitilin |  | Done
app.py (flask) revision + update | Everyone
homepage map (javascript + leaflet) | Bismaad | 2021-05-03
salaries (javascript + plotly) | Caitilin | 2021-05-03
third page visualization | Alannah
third factor research | Alannah | 2021-04-28
third factor data cleaning | Alannah
presentation | Caitilin
presentation practice | everyone | 2021-05-05
content for webpages | everyone
combine census tracts + income notebooks | Sara | 2021-04-28
merge census table + income table => load to db | Bismaad | 2021-04-28

## homepage
NavBar (bootstrap) = dropdown menu that is reactive to screen size
Map of Philadelphia (Leaflet) :
- census tracts
- Income information - popup
- education information (markers with school locations)
=> click on data point and navigate to other page
Text Box

## Page 2
NavBar (bootstrap) = dropdown menu that is reactive to screen size
Bar Chart (Plotly) - salary breakdown
- any other interesting trends
Text Box

## Page 3
NavBar (bootstrap) = dropdown menu that is reactive to screen size
Education Map
Text Box